## FYP2 Timeline
Task Description | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
Architecture review & backend refactoring | bar: W1 to W2
Spaced retention algorithm & decay calculations | bar: W3 to W4
AI study roadmap & multi-notebook selection | bar: W5 to W6
Timetable scanner & calendar sync integration | bar: W7 to W8
Spaced dispatcher & deep-link notifications | bar: W9 to W10
Mistakes bank & adaptive weakness remediation | bar: W11 to W12
Unit & integration test suites execution | bar: W13 to W14
Testing | bar: W13 to W14
Thesis documentation writing & revision | bar: W10 to W13
Final thesis submission | bar: W13
Presentation preparation & rehearsal | bar: W13 to W14
Final presentation & viva examination | bar: W14
Legend: | W8: Research & Development
Documentation & Prep
Milestone / Deliverable